## FFTT Cover Sheet
SUMP PLUS: Financial Framework & Tracker Tool
WORKED EXAMPLE
Please enter the time period for entering historic funding info (5-10 years)
Historic funding review period
| Timescale | 2004 -2024
| Number of years | 11
Implementation planning period
| Timescale | 2025 - 2030
| Number of years | 6
Version 1 (February 2023)

## Step 1 - Projection
SUMP PLUS Financial Framework and Tracker Tool: Worked Example
Step 1 - Projection of SUMP implementation budget
Review of SUMP spending by measure category
Funding source projection pivot table (source data from 'Measure Tracker' worksheet - do not edit) | [11 empty] | Calculation of projections (2025 to 2030) | [5 empty] | Funding allocations by measure sub-category Pivot Table (2014 - 2022) (source data from 'Measure Tracker' - do not edit) |  | Funding sources pivot table (2014 - 2022) (source data from 'Measure Tracker' - do not edit)
Row Labels | Sum of Funding (2014) | Sum of Funding (2015) | Sum of Funding (2016) | Sum of Funding (2017) | Sum of Funding (2018) | Sum of Funding (2019 | Sum of Funding (2020) | Sum of Funding (2021) | Sum of Funding (2022) | Sum of Funding (2023) | Sum of Funding (2024) | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Row Labels | Sum of TOTAL Funding | Row Labels | Sum of TOTAL Funding
EU Structural Funds |  |  | 500000 | 3000000 | [7 empty] | 318000 | 318000 | 318000 | 318000 | 318000 | 318000 | Highways network | 54000000 | EU Structural Funds | 3500000
Municipal budget | 7200000 | 10305000 | 12305000 | 12755000 | 11500000 | 20250000 | 11500000 | 10150000 | 9000000 | 6500000 | 6600000 | 10733000 | 10733000 | 10733000 | 10733000 | 10733000 | 10733000 | Highways works | 51500000 | Municipal budget | 118065000
(blank) | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Intelligent Traffic Management | 2500000 | (blank) | 0
EU (H2020 CIVITAS) | [6 empty] | 75000 | 75000 |  |  |  | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | Planning & Implementation Capacity | 150000 | EU (H2020 CIVITAS) | 150000
National climate mitigation fund | [7 empty] | 7500000 | 7500000 |  |  | 1364000 | 1364000 | 1364000 | 1364000 | 1364000 | 1364000 | SUMP Implementation Planning | 150000 | National climate mitigation fund | 15000000
EU URBACT | [7 empty] | 36000 | 14000 |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | Public Transport | 76265000 | EU URBACT | 50000
Municipal budget - tourism |  |  |  |  | 500000 | 500000 | 750000 | 750000 | 750000 | 750000 |  | 364000 | 364000 | 364000 | 364000 | 364000 | 364000 | Bus Rapid Transit (BRT) | 2100000 | Municipal budget - tourism | 4000000
Grand Total | 7200000 | 10305000 | 12805000 | 15755000 | 12000000 | 20750000 | 12325000 | 18511000 | 17264000 | 7250000 | 6600000 | 12797000 | 12797000 | 12797000 | 12797000 | 12797000 | 12797000 | Bus station and stops enhancements | 150000 | Grand Total | 140765000
[18 empty] | Inclusivity & accessibility | 15000
[18 empty] | Public Transport operational subsidies | 53000000
[18 empty] | Zero Carbon Bus Fleet | 21000000
[18 empty] | Walking and cycling | 10350000
[18 empty] | Walking and cycling networks | 8300000
Funding Source Duplicate table for chart creation (do not edit): | [17 empty] | Living Streets | 2050000
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Grand Total | 140765000
EU Structural Funds | 0 | 0 | 500000 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 318000 | 318000 | 318000 | 318000 | 318000 | 318000
Municipal budget | 7200000 | 10305000 | 12305000 | 12755000 | 11500000 | 20250000 | 11500000 | 10150000 | 9000000 | 6500000 | 6600000 | 10733000 | 10733000 | 10733000 | 10733000 | 10733000 | 10733000
(blank) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EU (H2020 CIVITAS) | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000
National climate mitigation fund | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500000 | 7500000 | 0 | 0 | 1364000 | 1364000 | 1364000 | 1364000 | 1364000 | 1364000
EU URBACT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 14000 | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
Municipal budget - tourism | 0 | 0 | 0 | 0 | 500000 | 500000 | 750000 | 750000 | 750000 | 750000 | 0 | 364000 | 364000 | 364000 | 364000 | 364000 | 364000
Grand Total | 7200000 | 10305000 | 12805000 | 15755000 | 12000000 | 20750000 | 12325000 | 18511000 | 17264000 | 7250000 | 6600000 | 12797000 | 12797000 | 12797000 | 12797000 | 12797000 | 12797000
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding by measure category pivot table (2014-2024) (source data from 'Measure Tracker' worksheet - do not edit)
Column Labels
Values | Highways network | Planning & Implementation Capacity | Public Transport | Walking and cycling | Grand Total
Sum of Funding (2014) | 3000000 |  | 4000000 | 200000 | 7200000
Sum of Funding (2015) | 6000000 |  | 3505000 | 800000 | 10305000
Sum of Funding (2016) | 8500000 |  | 3505000 | 800000 | 12805000
Sum of Funding (2017) | 11000000 |  | 4505000 | 250000 | 15755000
Sum of Funding (2018) | 6000000 |  | 4500000 | 1500000 | 12000000
Sum of Funding (2019 | 10500000 |  | 9000000 | 1250000 | 20750000
Sum of Funding (2020) | 8000000 | 75000 | 3500000 | 750000 | 12325000
Sum of Funding (2021) | 1000000 | 75000 | 16150000 | 1286000 | 18511000
Sum of Funding (2022) |  |  | 15500000 | 1764000 | 17264000
Sum of Funding (2023) |  |  | 5500000 | 1750000 | 7250000
Sum of Funding (2024) |  |  | 6600000 |  | 6600000

## Step 2 - Funding overview
SUMP PLUS Financial Framework and Tracker Tool: Worked Example
Step 2 - Estimate of SUMP implementation costs and funding sources/opportunities | [21 empty] | Grant funding |  |  | Finance |  | Property developer |  |  | Private mobility providers |  | Revenue options
[21 empty] | Comment on funding option utilisation and opportunities: | Continue previous success achieved in accessing Structural Funds and Horizon 2020 CIVITAS projects | No current funding calls announced. Relatively low level target included | No current funding calls announced | No current intentions to issue bonds | No current intentions to access loans | Long-term potential to introduce developer contribution mechanism, working with surrounding districts with suburban development (target based on 5,000Euros for 20 new houses/annum) | No site-specific requirements identified. | No monetary targets - policy covering walking and cycling standards (incl. cycle parking and changing facilities) to be introduced. | No monetary targets - employers to be approached through campaigns for eastern cycle corridor | No current plans - i.e. for shared mobility schemes | No current proposals | Increase charges at 500 city centre bays (estimate based on 2 Euro increase in revenue, 250 days per year) | No current proposals |  | Advertising revenue to be explored as option for BRT bus stop provision and maintenance. | Assumed equivalent access to municipal tax revenues
Measure Sub-categories | [8 empty] | Historic period: |  |  | Implementation planning period: | [6 empty] | Annual forecast budget - historic baseline: | 12796818.1818 | Historic annual average: | 0 | 1363636.3636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum of TOTAL Funding | Column Labels | [7 empty] | 2004 -2024 |  |  | 2025 - 2030 | [6 empty] | Annual forecast budget - target: | 12316666.6667 | Target annual funding: | 300000 | 500000 | 0 | 0 | 0 | 100000 | [5 empty] | 250000 |  |  | 166666.6667 | 11000000
Row Labels | EU Structural Funds | Municipal budget | (blank) | EU (H2020 CIVITAS) | National climate mitigation fund | EU URBACT | Municipal budget - tourism | Grand Total | Average funding per year | Historic average % funding per year | Row Labels | Sum of Estimated cost | Sum of Funding amount (from Step 3) | Balance (+/-) (from Step 3) | Average annual estimated cost | Comparison with historic average annual (+/-) | Baseline annual funding allocations | Planned average % funding per year | Baseline total funding allocation | Implementation plan balance (+/-) |  | EU | National Climate Fund | National 2 | Bonds | Loans | Land value capture/ developer contributions | Direct provision (in-kind) | Development standards | Employer direct provision | Mobility service provider | Congestion charges/ UVARs | Parking charges | Business subscriptions & fares | Personal subscriptions & fares | Advertising | Local taxation
Bus Rapid Transit (BRT) |  | 2100000 | 0 |  |  |  |  | 2100000 | 190909.0909 | 1.4918 | Bus Rapid Transit (BRT) | 13050000 | 0 | -13050000 | 2175000 | -1984090.9091 | 2166666.67 | 32.423 | 13000000.02 | -49999.98 |  | 300000 | 400000 |  |  |  | 50000 | [8 empty] | 166667 | 1249999.67
Bus station and stops enhancements |  | 150000 | [5 empty] | 150000 | 13636.3636 | 0.10656 | Bus station and stops enhancements | 0 | 0 | 0 | 0 | 13636.3636 | 0 | 0 | 0 | 0
Highways works | 3500000 | 48000000 | [5 empty] | 51500000 | 4681818.1818 | 36.5858 | Highways works | 0 | 0 | 0 | 0 | 4681818.1818 | 0 | 0 | 0 | 0
Inclusivity & accessibility |  | 15000 | [5 empty] | 15000 | 1363.6364 | 0.010656 | Inclusivity & accessibility | 0 | 0 | 0 | 0 | 1363.6364 | 0 | 0 | 0 | 0
Intelligent Traffic Management |  | 2500000 | [5 empty] | 2500000 | 227272.7273 | 1.776 | Intelligent Traffic Management | 0 | 0 | 0 | 0 | 227272.7273 | 0 | 0 | 0 | 0
Walking and cycling networks |  | 4300000 | 0 |  |  |  | 4000000 | 8300000 | 754545.4545 | 5.8964 | Walking and cycling networks | 4595000 | 0 | -4250000 | 765833.3333 | -11287.8788 | 765833.33 | 11.4603 | 4594999.98 | -0.02 |  |  | 100000 |  |  |  | 50000 | [5 empty] | 250000 |  |  |  | 365833.33
SUMP Implementation Planning |  |  |  | 150000 |  |  |  | 150000 | 13636.3636 | 0.10656 | SUMP Implementation Planning | 0 | 0 | 0 | 0 | 13636.3636 | 0 | 0 | 0 | 0
Public Transport operational subsidies |  | 53000000 | [5 empty] | 53000000 | 4818181.8182 | 37.6514 | Public Transport operational subsidies | 21500000 | 0 | -21500000 | 3583333.3333 | 1234848.4848 | 3583333.33 | 53.6226 | 21499999.98 | -0.02 | [16 empty] | 3583333.33
Zero Carbon Bus Fleet |  | 6000000 |  |  | 15000000 |  |  | 21000000 | 1909090.9091 | 14.9185 | Zero Carbon Bus Fleet | 0 | 0 | 0 | 0 | 1909090.9091 | 0 | 0 | 0 | 0
Living Streets |  | 2000000 |  |  |  | 50000 |  | 2050000 | 186363.6364 | 1.4563 | Living Streets | 0 | 0 | 0 | 0 | 186363.6364 | 0 | 0 | 0 | 0
Active mobility to BRT |  |  | 0 |  |  |  |  | 0 | 0 | 0 | Active mobility to BRT | 1000000 | 0 | -1000000 | 166666.6667 | -166666.6667 | 166666.67 | 2.4941 | 1000000.02 | 0.02 | [16 empty] | 166666.67
Sub-category 12 | [8 empty] | 0 | 0 | Sub-category 12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 13 | [8 empty] | 0 | 0 | Sub-category 13 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 14 | [8 empty] | 0 | 0 | Sub-category 14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 15 | [8 empty] | 0 | 0 | Sub-category 15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 16 | [8 empty] | 0 | 0 | Sub-category 16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 17 | [8 empty] | 0 | 0 | Sub-category 17 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 18 | [8 empty] | 0 | 0 | Sub-category 18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 19 | [8 empty] | 0 | 0 | Sub-category 19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 20 | [8 empty] | 0 | 0 | Sub-category 20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 21 | [8 empty] | 0 | 0 | Sub-category 21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 22 | [8 empty] | 0 | 0 | Sub-category 22 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 23 | [8 empty] | 0 | 0 | Sub-category 23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 24 | [8 empty] | 0 | 0 | Sub-category 24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 25 | [8 empty] | 0 | 0 | Sub-category 25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 26 | [8 empty] | 0 | 0 | Sub-category 26 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 27 | [8 empty] | 0 | 0 | Sub-category 27 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 28 | [8 empty] | 0 | 0 | Sub-category 28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 29 | [8 empty] | 0 | 0 | Sub-category 29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Sub-category 30 | [8 empty] | 0 | 0 | Sub-category 30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 3500000 | 118065000 | 0 | 150000 | 15000000 | 50000 | 4000000 | 140765000 | 12796818.1818 |  | Grand Total | 40145000 | 0 | -39800000 | 6690833.3333 | -6690833.3333 | 6682500 |  | 40095000 |  | Check sub-totals: | 300000 | 500000 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 166667 | 5365833
Duplicate table for chart creation (do not edit): | [20 empty] | Duplicate table for chart creation (do not edit):
Measure Sub-category | Historic average % funding per year | Planned average % funding per year | [18 empty] | Funding source | EU | National Climate Fund | National 2 | Bonds | Loans | Land value capture/ developer contributions | Direct provision (in-kind) | Development standards | Employer direct provision | Mobility service provider | Congestion charges/ UVARs | Parking charges | Business subscriptions & fares | Personal subscriptions & fares | Advertising | Local taxation
Bus Rapid Transit (BRT) | 1.4918 | 32.423 | [18 empty] | Funding amount | 300000 | 500000 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0 | 166666.6667 | 11000000
Bus station and stops enhancements | 0.10656 | 0
Highways works | 36.5858 | 0
Inclusivity & accessibility | 0.010656 | 0
Intelligent Traffic Management | 1.776 | 0
Walking and cycling networks | 5.8964 | 11.4603
SUMP Implementation Planning | 0.10656 | 0
Public Transport operational subsidies | 37.6514 | 53.6226
Zero Carbon Bus Fleet | 14.9185 | 0
Living Streets | 1.4563 | 0
Active mobility to BRT | 0 | 2.4941
Sub-category 12 | 0 | 0
Sub-category 13 | 0 | 0
Sub-category 14 | 0 | 0
Sub-category 15 | 0 | 0
Sub-category 16 | 0 | 0
Sub-category 17 | 0 | 0
Sub-category 18 | 0 | 0
Sub-category 19 | 0 | 0
Sub-category 20 | 0 | 0
Sub-category 21 | 0 | 0
Sub-category 22 | 0 | 0
Sub-category 23 | 0 | 0
Sub-category 24 | 0 | 0
Sub-category 25 | 0 | 0
Sub-category 26 | 0 | 0
Sub-category 27 | 0 | 0
Sub-category 28 | 0 | 0
Sub-category 29 | 0 | 0
Sub-category 30 | 0 | 0

## Step 3 - Measure Tracker
SUMP PLUS Financial Framework and Tracker Tool: Worked Example
Step 3 - Action & Budget Tracker
|  | Programme name (i.e. SUMP) | Brief measure description | Sub-divisions of complex measures andseparate records of measure funding sources | Enables geogra | phical clusteruing and filtering of measures | Current measure stage: Concept; Plan, Design & Implement; Operation |  | 2004 -2024 |  |  | Implementation Planning: |  | 2025 - 2030 | 2014 |  |  | 2015 |  |  | 2016 |  |  | 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028 |  |  | 2029 |  |  | 2030 |  |  | 2031 |  |  | 2032 |  |  | 2033
Category | Sub-category | Programme | Measure | Activity / Funding source | Package/cluster | Status / priority | Status (2023) | Responsibility | TOTAL funding | Funding source | Funding purpose | Estimated cost | Funding amount | Balance (+/-) | Phase (2014) | Cost Estimate (2014) | Funding (2014) | Phase (2015) | Cost Estimate (2015) | Funding (2015) | Phase (2016) | Cost Estimate (2016) | Funding (2016) | Phase (2017) | Cost Estimate (2017) | Funding (2017) | Phase (2018) | Cost Estimate (2018) | Funding (2018) | Phase (2019) | Cost Estimate (2019) | Funding (2019 | Phase (2020) | Cost Estimate (2020) | Funding (2020) | Phase (2021) | Cost Estimate (2021) | Funding (2021) | Phase (2022) | Cost Estimate (2022) | Funding (2022) | Phase (2023) | Cost Estimate (2023) | Funding (2023) | Phase (2024) | Cost Estimate (2024) | Funding (2024) | Phase (2025) | Cost Estimate (2025) | Funding (2025) | Phase (2026) | Cost Estimate (2026) | Funding (2026 | Phase (2027) | Cost Estimate (2027) | Funding (2027) | Phase (2028) | Cost Estimate (2028) | Funding (2028) | Phase (2029) | Cost Estimate (2029) | Funding (2029) | Phase (2030) | Cost Estimate (2030) | Funding (2030) | Phase (2031) | Cost Estimate (2031) | Funding (2031) | Phase (2032) | Cost Estimate (2032) | Funding (2032) | Phase (2033) | Cost Estimate (2033) | Funding (2033)
Highways network | Intelligent Traffic Management | - | Implementation of coordinated traffic control system and management centre | Traffic light installation works of the prepared project |  | Complete | Operation | Municipal authority; Transport Department | 2500000 | Municipal budget | Plan & Implement | 0 | 0 | 0 | [15 empty] | IMPL |  | 500000 | IMPL |  | 1000000 | IMPL |  | 1000000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Highways network | Highways works | - | Increase capacity of street network: central, northern and coastal areas | Street modernisation: central, northern and coastal areas | - | Complete | Operation | Municipal authority; Transport Department | 48000000 | Municipal budget | Plan & Implement | 0 | 0 | 0 | IMPL |  | 3000000 | IMPL |  | 6000000 | IMPL |  | 8000000 | IMPL |  | 8000000 | IMPL |  | 6000000 | IMPL |  | 10000000 | IMPL |  | 7000000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Highways network | Highways works | - | Reducation of air particulate pollution | Updating street maintenance and cleaning technologies | - | Complete | Operation | Municipal authority; Transport Department | 1500000 | EU Structural Funds | Operation | 0 | 0 | 0 | [9 empty] | IMPL |  | 1500000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Highways network | Highways works | - | Reconstruction of railway crossing | Improvements to vehicle and pedestrian safety | - | Complete | Operation | Municipal authority; Transport Department | 2000000 | EU Structural Funds | Plan & Implement | 0 | 0 | 0 | [6 empty] | IMPL |  | 500000 | IMPL |  | 1500000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Planning & Implementation Capacity | SUMP Implementation Planning | SUMP | CIVITAS City Lab | Preparation of Implementation Plan for BRT and cycle highway corridors | - | Complete | Operation | Municipal authority; Transport Department | 150000 | EU (H2020 CIVITAS) | Plan & Implement | 0 | 0 | 0 | [18 empty] | DES |  | 75000 | DES |  | 75000
Public Transport | Public Transport operational subsidies | - | Subsidies to cover standard PT operational costs | Increased subsidies required during COV19 pandemic due to fare revenue shortfall | - | Ongoing | Operation | Municipal authority; Transport Department | 53000000 | Municipal budget | Operation | 21500000 | 0 | -21500000 | OP |  | 4000000 | OP |  | 3500000 | OP |  | 3500000 | OP |  | 4500000 | OP |  | 4500000 | OP |  | 3000000 | OP |  | 3500000 | OP |  | 8500000 | OP |  | 8000000 | OP |  | 5500000 | OP |  | 4500000 | OP | 4000000 |  | OP | 3500000 |  | OP | 3500000 |  | OP | 3500000 |  | OP | 3500000 |  | OP | 3500000
Public Transport | Inclusivity & accessibility | - | Installation of guidance systems for visually impaired people | Installation on High Street as priority | - | Complete | Operation | Municipal authority; Transport Department | 15000 | Municipal budget | Plan & Implement | 0 | 0 | 0 |  |  |  | IMPL |  | 5000 | IMPL |  | 5000 | IMPL |  | 5000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Public Transport | Zero Carbon Bus Fleet | SUMP | Procurement of electric buses | Replacement of existing buses - municipal funds |  | Complete | Operation | Municipal authority; Transport Department | 6000000 | Municipal budget | Plan & Implement | 0 | 0 | 0 | [12 empty] | IMPL |  |  | IMPL |  | 6000000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Public Transport | Zero Carbon Bus Fleet | SUMP | Procurement of electric buses | Replacement of existing buses - national climate mitigation fund |  | Complete | Operation | Municipal authority; Transport Department | 15000000 | National climate mitigation fund | Plan & Implement | 0 | 0 | 0 | [21 empty] | IMPL |  | 7500000 | IMPL |  | 7500000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Public Transport | Bus station and stops enhancements | SUMP | Refurbishment of Old Market interchange bus stop facilities | - | - | Complete |  | Municipal authority; Transport Department | 150000 | Municipal budget | Plan & Implement | 0 | 0 | 0 | [21 empty] | IMPL |  | 150000 | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP |  |  | OP
Public Transport | Bus Rapid Transit (BRT) | SUMP | BRT north-south corridor | BRT highway priority measures at key junctions on main boulevard | Main boulevard | Approved | Implement | Municipal authority; Transport Department | 1500000 | Municipal budget | Plan & Implement | 6500000 | 0 | -6500000 | [30 empty] | IMPL |  | 1500000 | IMPL | 3500000 |  | IMPL | 3000000 |  | OP |  |  | OP |  |  | OP |  |  | OP
Public Transport | Bus Rapid Transit (BRT) | SUMP | BRT north-south corridor | BRT modernisation of traffic control equipment to provide "green wave" on main boulvard | Main boulevard | Approved | Implement | Municipal authority; Transport Department | 400000 | Municipal budget | Plan & Implement | 1600000 | 0 | -1600000 | [30 empty] | IMPL |  | 400000 | IMPL | 800000 |  | IMPL | 800000 |  | OP |  |  | OP |  |  | OP |  |  | OP
Public Transport | Bus Rapid Transit (BRT) | SUMP | BRT north-south corridor | Design and installation of new BRT passenger stops on north-south corridor | Main boulevard | Approved | Implement | Municipal authority; Transport Department | 200000 | Municipal budget | Plan & Implement | 1000000 | 0 | -1000000 | [30 empty] | DES |  | 200000 | IMPL | 500000 |  | IMPL | 500000 |  | OP |  |  | OP |  |  | OP |  |  | OP
Public Transport | Bus Rapid Transit (BRT) | SUMP | BRT north-south corridor | Creation of Park & Ride facility at nothern terminal of BRT corridor | Main boulevard | Approved | Implement | Municipal authority; Transport Department | 0 |  | Plan & Implement | 2500000 | 0 | -2500000 | [33 empty] | IMPL | 500000 |  | IMPL | 1000000 |  | IMPL | 1000000 |  | OP |  |  | OP |  |  | OP
Public Transport | Bus Rapid Transit (BRT) | SUMP PLUS | BRT north-south corridor | Camera-based bus lane enforcement | Main boulevard | Concept |  | Municipal authority; Transport Department | 0 |  | Plan & Implement | 500000 | 0 | -500000 | [34 empty] | 50000 |  | IMPL | 400000 |  | IMPL | 50000 |  | OP |  |  | OP |  |  | OP
Public Transport | Bus Rapid Transit (BRT) | SUMP PLUS | BRT north-south corridor | BRT Marketing Campaign | Main boulevard | Concept |  | Municipal authority; Transport Department | 0 |  | Plan & Implement | 350000 | 0 | -350000 | [36 empty] | PLAN | 50000 |  | IMPL | 150000 |  | IMPL | 150000
Public Transport | Bus Rapid Transit (BRT) | SUMP PLUS | BRT north-south corridor | Relocation of parking spaces along BRT route, and effective enforcement | Main boulevard | Concept |  | Municipal authority; Transport Department | 0 |  | Plan & Implement | 600000 | 0 | -600000 | [36 empty] | DES | 100000 |  | IMPL | 200000 |  | IMPL | 200000 |  | OP | 50000 |  | OP | 50000
Walking and cycling | Active mobility to BRT | SUMP PLUS | BRT north-south corridor - high quality pedestrian routes to bus stops | A.2.2 Supporting measure: Provision of safe and well-lit walking routes to BRT stops | Main boulevard | Concept |  | Municipal authority; Transport Department | 0 |  | Plan & Implement | 1000000 | 0 | -1000000 | [33 empty] | DES | 250000 |  | IMPL | 250000 |  | IMPL | 250000 |  | IMPL | 250000
Walking and cycling | Living Streets | SUMP | Pilot of 'Living Streets' concept in residential quarter, Old Town |  | Old Town | Complete |  | Municipal authority; Transport Department | 50000 | EU URBACT | Plan & Implement | 0 | 0 | 0 | [21 empty] | IMPL |  | 36000 | IMPL |  | 14000
Walking and cycling | Living Streets | SUMP | Old Town enhancements for pedestrians, cyclists and disabled access |  | Old Town | Complete |  | Municipal authority; Transport Department | 2000000 | Municipal budget | Plan & Implement | 0 | 0 | 0 | [9 empty] | IMPL |  | 250000 | IMPL |  | 1000000 | IMPL |  | 750000
Walking and cycling | Walking and cycling networks | SUMP | Repair and installation works of pedestrian and bicycle paths, sidewalks |  | Coastal zone | Complete |  | Municipal authority; Transport Department | 4000000 | Municipal budget - tourism | Plan & Implement | 0 | 0 | 0 | [12 empty] | DES |  | 500000 | IMPL |  | 500000 | IMPL |  | 750000 | IMPL |  | 750000 | IMPL |  | 750000 | IMPL |  | 750000
Walking and cycling | Walking and cycling networks | SUMP | Repair and enhancement works for existing pedestrian and bicycle paths |  | Southern district | Complete |  | Municipal authority; Transport Department | 2500000 | Municipal budget | Plan & Implement | 0 | 0 | 0 | [21 empty] | DES |  | 500000 | IMPL |  | 1000000 | IMPL |  | 1000000
Walking and cycling | Walking and cycling networks | SUMP | New cycle superhighway from eastern suburbs to city centre | Installation of new segregated bicycle lane linking Southern district with main boulevard | Eastern cycle corridor | Approved |  | Municipal authority; Transport Department | 0 |  |  | 4250000 | 0 | -4250000 | [39 empty] | DES | 250000 |  | IMPL | 2000000 |  | IMPL | 2000000
Walking and cycling | Walking and cycling networks | SUMP PLUS | Cycle parking: for new cycle superhighway from eastern suburbs to city centre | Installation of bicycle parking at key locations along cycle superhighway | Eastern cycle corridor | Concept |  | Municipal authority; Transport Department | 0 |  |  | 45000 | [41 empty] | IMPL | 15000 |  | IMPL | 15000 |  | IMPL | 15000
Walking and cycling | Walking and cycling networks | SUMP PLUS | Campaign working with major employers: for use of new cycle superhighway from eastern suburbs to city centre | Campaign working in partnership with major employers to promote cycle commuting, including on-site provision of cycle parking and changing facilities. | Eastern cycle corridor | Concept |  | Municipal authority; Transport Department | 0 |  |  | 150000 | [44 empty] | PLAN | 50000 |  | IMPL | 50000 |  | IMPL | 50000
Walking and cycling | Walking and cycling networks | SUMP PLUS | Campaign working with schools: for use of new cycle superhighway from eastern suburbs to city centre | Campaign working in partnership with schools to promote cycle trips to school, including: cycle safety lessons; cycling events; and on-site provision of parking and changing facilities | Eastern cycle corridor | Concept |  | Municipal authority; Transport Department | 0 |  |  | 150000 | [44 empty] | PLAN | 50000 |  | IMPL | 50000 |  | IMPL | 50000
Walking and cycling | Walking and cycling networks | SUMP | Installation of missing sections of bicycle lanes |  | Southern district | Complete |  | Municipal authority; Transport Department | 1800000 | Municipal budget | Plan & Implement | 0 | 0 | 0 |  |  | 200000 |  |  | 800000 |  |  | 800000
Public Transport | Sub-category 12
Public Transport | Sub-category 13
Public Transport | Sub-category 14
Public Transport | Sub-category 15
Planning & Implementation Capacity | Sub-category 16
Planning & Implementation Capacity | Sub-category 17
Planning & Implementation Capacity | Sub-category 18
Planning & Implementation Capacity | Sub-category 19
Sustainable mobility campaigns | Sub-category 20
Sustainable mobility campaigns | Sub-category 21
Sustainable mobility campaigns | Sub-category 22
Sustainable mobility campaigns | Sub-category 23
Sustainable mobility campaigns | Sub-category 24
Shared mobility | Sub-category 25
Shared mobility | Sub-category 26
Shared mobility | Sub-category 27
Shared mobility | Sub-category 28
Walking and cycling | Sub-category 29
Walking and cycling | Sub-category 30
Note on AG6: Timothy Durant: Based on 8,524,100Euros divided by six activities.
Note on AJ6: Timothy Durant: Based on 24,784,700Euros divided by six activities
Note on AM9: Timothy Durant: PORTIS + SUMP PLUS